## Sheet1
Task | Hours | Notes | Done/Not Done
Displayed information from the database on a web app | 3 |  | Done | http://www.mytecbits.com/microsoft/dot-net/bootstrap-3-0-0-with-asp-net-web-forms
Research on Bootstrap | 5 | Look into how to scale for mobile phones | Done | http://www.monodevelop.com/screenshots/
Upload web app onto github | 0 |  | Not Done | http://www.w3schools.com/bootstrap/bootstrap_pager.asp
Research hosting web app on Amazon EC2 | 1 |  | Not Done
Research on hosting a database on Amazon RDS | 0 |  | Not Done
Establish connection to postgresql database | 1 |  | Done
Jquery Mobile | 1 |  | Done
Research on application of Bootstrap | 2 |  | Done
Started implementing Bootstrap w/ ASP.NET | 4 |  | Done
Create login/signup page | 0 |  | Done
Work with visuals on scratch paper | 1 | Front-End | Done
Work on database backend on scratch paper | 2 | ERD Model/Relationships | Done
Made request to postgres database from front-end | 2 |  | Done
Create Login Page | 3.5 |  | Done
Create SignUp and Update Login Page | 2 |  | Done
Fixed bug with uploading images (bytea) to database | 3 |  | Done
Work on pagination and getting that working |  |  | Done
Making necessary links re-directable | 1 |  | Done
Bug Fixes on importing images | 5 |  | Done
Import list of colleges | 1 |  | Done
Fixed sign-off button | 1 |  | Done
Watched video on Master Pages and wrote down list todo | 1 |  | Done
Fix paging for collections page and added additional redirects | 5 |  | Done
Started creating a webpage to upload textbook information | 1 |  | Done
Fixed bugs from Collections, adding books, login, sign up page | 8 |  | Done
Set up redirecting pages, encryption for password through HASH | 3 |  | Done
Setup conditions for uploading textbooks and signing in | 1 |  | Done
Cleaned up website | 2 |  | Done
Research uploading web project to web server | 2 |  | Not Done
Create ERD picture | 0 |  | Done
Research to upload database to web/database server | 0 |  | Not Done